SAFETYNEXUS

AI-Powered Domestic Violence Practice Support Platform

Project Proposal & Sprint-Based Development Estimate  |  March 2026

# 1. Project Overview

SafetyNexus is a SaaS digital coaching platform built exclusively on the Safe & Together (S&T) model. It is designed to support domestic violence caseworkers and the organizations that employ them — serving as a persistent, intelligent practice partner accessible 24/7 through a browser-based chat interface.

The platform addresses a critical gap: caseworkers handling high-stakes domestic violence cases often lack real-time access to expert guidance. They work under intense pressure, face emotional burnout, and may inadvertently apply practice that drifts from the S&T model — placing survivors and children at greater risk.

SafetyNexus puts an always-available, model-trained AI coach in every caseworker's pocket. Every interaction — coaching, role-play, case mapping, survivor support, well-being — is grounded in the S&T framework. The tool does not offer generic advice. It is a S&T-specific practice environment.

# 2. What is the Safe & Together (S&T) Model?

The Safe & Together model is a globally recognised professional framework for domestic violence intervention. Its core principle is:

"Focus on what the perpetrator is doing — not on blaming the survivor (mother/non-offending parent)."

Most systems inadvertently place responsibility on the victim ('Why didn't she leave?'). The S&T model reframes this: document the perpetrator's pattern of behavior, recognize the survivor's protective actions, and keep children safe by holding the abuser accountable. SafetyNexus is built to ensure caseworkers consistently apply this model — and are gently corrected when they drift from it.

# 3. Platform Type & Scope

SafetyNexus is a web-based SaaS platform — browser-based, accessible from desktop, tablet, and mobile without any app installation. It operates as a multi-tenant system where each deploying organization (e.g., a government DV agency) gets their own isolated, branded instance.

This is a greenfield build — development starts from scratch. The document provided (v0.3, February 2026) is a full product specification covering architecture, all modules, security, compliance, analytics, and Beta success criteria.

## Target Deployment Markets (Beta)

- Scotland (UK GDPR + Scottish statutory reporting requirements)

- New Zealand (NZ Privacy Act 2020)

- Australia (Australian Privacy Act 1988)

## Platform Type

- Web application (browser-based) — Phase 1 and 2

- Mobile app (iOS/Android) — Phase 4 only (not in scope for this estimate)

- API-first architecture required from day one for future CMS integrations

# 4. Modules Overview

SafetyNexus consists of 8 core modules. All modules are required for Beta launch.

| # | Module | Purpose |
| --- | --- | --- |
| 1 | The Coach | AI chat coach grounded exclusively in S&T model with fidelity drift detection |
| 2 | Role-Play Simulator | Practice conversations with AI personas + debrief feedback |
| 3 | Case Mapping Tool (12-Step) | Guided perpetrator pattern documentation with document upload + PDF export |
| 4 | Survivor Partnering Framework | Step-by-step coaching on survivor-centered communication |
| 5 | Well-Being Companion | Emotional support, distress detection, hardcoded crisis protocol |
| 6 | Analytics & Reporting Dashboard | Usage metrics, NLP theme detection, fidelity signals (anonymized) |
| 7 | Admin & Localization Console | Per-org branding, doc library, user management, crisis resource config |
| 8 | Document Library Integration | Upload org docs into AI knowledge base; future: SharePoint/Drive sync |

# 5. Recommended Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js + React + Tailwind CSS | Chat UI, dashboards, admin console |
| Backend | Python FastAPI | API-first architecture, all module logic |
| AI / LLM | GPT-4 + RAG | Coach, role-play, fidelity monitoring |
| Vector Database | Pinecone / Weaviate | S&T knowledge base retrieval |
| Primary Database | PostgreSQL (multi-tenant) | User data, session history, case maps |
| Cloud Infrastructure | AWS or Azure (multi-region) | Data residency: EU, UK, AU, US |
| File Storage | AWS S3 / Azure Blob | Document uploads, PDF exports |
| NLP / Analytics | spaCy or AWS Comprehend | Theme detection on anonymized data |
| Monitoring | Datadog / New Relic | Performance, uptime, security events |

Note: Final tech stack selections (cloud provider, LLM provider) to be confirmed at Sprint 1 kickoff session.

# 6. Sprint-Based Development Estimate

Development is organized into 7 sprints. Each sprint = 2 weeks. Total estimated duration: 14 weeks (~3.5 months) to full development completion, followed by deployment.

| Sprint | Timeline | Phase | Key Deliverable |
| --- | --- | --- | --- |
| Sprint 1 | Weeks 1–2 | Foundation, Infrastructure & AI Coach | Deployable app with login, roles, and fully functional AI Coach with S&T knowledge base |
| Sprint 2 | Weeks 3–4 | Role-Play Simulator & Case Mapping Tool | Role-play simulator with personas + debrief, and fully functional case mapping tool |
| Sprint 3 | Weeks 5–6 | Survivor Partnering, Well-Being & Crisis Protocol | Survivor Partnering, Well-Being, and crisis protocol modules fully operational |
| Sprint 4 | Weeks 7–8 | User Roles, Memory, Admin Console & Localization | All user roles, persistent memory, admin console, and full localization working |
| Sprint 5 | Weeks 9–10 | Analytics Dashboard & Reporting | Full analytics dashboard with NLP theme detection, fidelity signals, and privacy controls |
| Sprint 6 | Weeks 11–12 | Security, Compliance, Onboarding & AI Safety | Security-hardened, GDPR-compliant, accessible platform with AI safety layer and onboarding |
| Sprint 7 | Weeks 13–14 | QA, Performance Testing & Pre-Deployment Handover | Fully tested, QA-passed platform ready for deployment — client sign-off obtained |

7. Detailed Sprint Breakdown

Each sprint below lists all user stories and the sprint deliverable.

Sprint 1  |  Weeks 1–2  Foundation, Infrastructure & AI Coach

- Cloud infrastructure setup (multi-tenant AWS/Azure), CI/CD pipeline, dev/staging/prod environments

- Database schema design (multi-tenant PostgreSQL), domain, SSL, environment config

- Base project structure (Next.js frontend + FastAPI backend), authentication (email/password, RBAC)

- LLM API integration (Claude/GPT-4 with RAG architecture)

- S&T knowledge base ingestion into vector database (Pinecone)

- Chat UI — full-screen conversational interface with context hot-buttons

- Session persistence, fidelity drift detection, AI redirection logic

✓ Sprint Deliverable: Deployable app with login, roles, and fully functional AI Coach with S&T knowledge base

Sprint 2  |  Weeks 3–4  Role-Play Simulator & Case Mapping Tool

- Role-play mode UI, AI persona engine (survivor, perpetrator, judge, police, supervisor, child)

- 10 pre-built scenario templates, real-time coach observation during role-play

- Post role-play debrief with S&T-aligned feedback, distress trigger detection

- 12-step guided case mapping form with conversational prompts

- Document upload (PDF, DOCX, TXT), AI pre-population of case map fields

- Worker review/edit interface, case map save/resume/progress tracking

- Multi-case support, PDF export of completed case maps

✓ Sprint Deliverable: Role-play simulator with personas + debrief, and fully functional case mapping tool

Sprint 3  |  Weeks 5–6  Survivor Partnering, Well-Being & Crisis Protocol

- Survivor Partnering module — step-by-step guided framework and language suggestions

- Well-Being Companion: automatic and manual activation, distress detection

- Survivor-professional recognition (worker personal disclosure handling)

- Hardcoded crisis protocol: Category A (personal safety), B (mental health), C (child danger)

- Jurisdiction-specific crisis resource display (Scotland, NZ, AU)

- Privacy enforcement: well-being sessions excluded from all analytics

- Transition flows between all modules (coach ↔ role-play ↔ well-being ↔ mapping)

✓ Sprint Deliverable: Survivor Partnering, Well-Being, and crisis protocol modules fully operational

Sprint 4  |  Weeks 7–8  User Roles, Memory, Admin Console & Localization

- Full RBAC (5 roles), supervisor team assignment, persistent cross-session memory per user

- Memory application: case context awareness, growth tracking, session summaries

- Dashboard home screen (recent sessions, case maps, quick-start buttons), PII protection

- Admin console: org branding, document library management, localization layers 1–3

- Local knowledge base — org documents injected into AI context per tenant

- Bulk user import (CSV), invitation flow, user management, role assignment

- Crisis resource config per tenant, conflict detection (local vs core S&T content)

✓ Sprint Deliverable: All user roles, persistent memory, admin console, and full localization working

Sprint 5  |  Weeks 9–10  Analytics Dashboard & Reporting

- Usage metrics dashboard: sessions, duration, module breakdown, active vs registered users

- NLP theme detection (topic modeling on anonymized conversation data)

- Practice fidelity signals (aggregate, anonymized) and well-being volume signals

- Multi-level access: worker / supervisor / manager dashboard views

- Charts, trend lines, heat maps, time-period filters

- PDF and CSV export of reports

- Privacy enforcement: no individual session data exposed in any dashboard

✓ Sprint Deliverable: Full analytics dashboard with NLP theme detection, fidelity signals, and privacy controls

Sprint 6  |  Weeks 11–12  Security, Compliance, Onboarding & AI Safety

- AES-256 encryption at rest, TLS 1.2+, MFA (TOTP), SSO (SAML 2.0 / OAuth 2.0)

- Data residency configuration (EU, UK, AU, US), GDPR right-to-erasure, audit logging

- WCAG 2.1 AA accessibility audit and fixes, performance optimization (coach <5s)

- First-login onboarding flow (10–15 min), module orientation, prompt writing guidance

- Account lifecycle: worker/org offboarding, data export, suspension/reinstatement

- Session/case map search (keyword, date, module filter), bookmarking

- Response flagging (thumbs up/down, fidelity flag, harmful flag), hallucination guardrails

- Red-teaming: mother-blaming, perpetrator persona abuse, out-of-scope queries

✓ Sprint Deliverable: Security-hardened, GDPR-compliant, accessible platform with AI safety layer and onboarding

Sprint 7  |  Weeks 13–14  QA, Performance Testing & Pre-Deployment Handover

- End-to-end QA across all 8 modules and all 5 user roles

- Cross-browser and mobile responsive testing

- Load testing: 500 concurrent users, 2x and 5x peak, auto-scaling validation

- Data backup and recovery testing (RTO <4hrs, RPO <1hr)

- Third-party penetration testing and final security audit

- Uptime monitoring, status page setup, and error alerting configuration

- Legal review: ToS, Privacy Policy, DPA templates finalized and signed off

- Bug fixes, final optimizations, and staging environment sign-off

- Deployment documentation, runbooks, and handover package prepared

- Client UAT (User Acceptance Testing) on staging environment

✓ Sprint Deliverable: Fully tested, QA-passed platform ready for deployment — client sign-off obtained

# 8. Project Timeline Summary

| Phase | Timeline | Milestone |
| --- | --- | --- |
| Full Development | Weeks 1–14 | All 8 modules built, tested, QA-passed, and client sign-off obtained |
| Deployment | Post Week 14 | Production deployment, pilot org setup (Scotland, NZ, AU), and go-live |
| GA Decision | 90 Days Post-Launch | Leadership review: all Beta success benchmarks assessed |
| Phase 2 — Pilots | Post-Week 37 | Enhanced analytics, SSO, statutory reporting, survivor partnering enhancements |
| Phase 3 — GA | TBD | Full feature set, CMS integrations, multi-language support |
| Phase 4 — Scale | TBD | Mobile apps, predictive analytics, global expansion |

# 9. Client Responsibilities & Assumptions

The following items are required from the client side to keep development on schedule:

- 1. Client (David Mandel / Ruth) to provide all S&T knowledge base content prior to Sprint 2

- 2. Client to review and approve all AI knowledge base content before Beta launch

- 3. Client to provide jurisdiction-specific crisis resource data for Scotland, NZ, and Australia

- 4. Legal counsel (client-side) to review and approve ToS, DPA, and crisis protocol before Beta

- 5. Client to provide organization-specific policy documents for localization templates

- 6. All role-play persona profiles and scenario scripts to be supplied/approved by S&T subject matter experts

- 7. Cloud provider selection (AWS or Azure) to be finalized in Sprint 1 kickoff

- 8. LLM provider (Anthropic Claude or OpenAI GPT-4) to be confirmed before Sprint 2

- 9. Third-party penetration testing vendor to be engaged by client prior to Sprint 9

- 10. Pilot organizations (Scotland, NZ, AU) to be identified and onboarding-ready before Sprint 12

# 10. Key Risks & Mitigations

| Risk | Severity | Mitigation |
| --- | --- | --- |
| AI produces model-inconsistent (harmful) responses | Critical | RAG architecture + red-teaming + fidelity review before Beta launch |
| S&T knowledge base content delayed by client | High | Sprint 2 cannot start without approved content — agree delivery dates at kickoff |
| Legal review not completed before Beta launch | High | Engage legal counsel in parallel from Sprint 6 — not post-development |
| Data residency requirements differ across jurisdictions | Medium | Multi-region cloud architecture from Sprint 1; per-tenant encryption key management |
| Worker distress escalates during Well-Being session | High | Hardcoded crisis protocol (non-AI) tested and reviewed by legal before Beta |
| Performance degradation at scale (500+ concurrent users) | Medium | Load testing at 2x and 5x peak in Sprint 7; auto-scaling infrastructure |

# 11. Conclusion

SafetyNexus is a complex, high-stakes AI platform that requires precision in both engineering and content. The 7-sprint, 14-week estimate covers the complete Beta build — from infrastructure to AI safety, compliance, and pilot deployment.

The most critical success factors are: (1) the AI must produce only S&T-aligned responses, (2) the crisis protocol must be legally sound and hardcoded, and (3) privacy architecture must be watertight across all user roles and jurisdictions.

With a dedicated team, timely content delivery from the S&T subject matter experts, and early legal engagement, SafetyNexus can complete full development within 3.5 months, followed by production deployment, and deliver genuine impact for caseworkers and the vulnerable families they serve.

Prepared by: Development Team

Date: March 2026